## Slide 1
1. CANADEM has a high tolerance for operational risks
  Utility for UN, GoC and others, as CANADEM is willing to accept certain risks that they need to transfer.
  Successful management of substantial risk transferred from the UN, GoC and others has created a resilient organization confident in its Integrated Risk Management capacity.
2. CANADEM is fiscally cautious and financially risk-adverse
  A CANADEM financial management principle is that almost always it is expending taxpayers’ funds, and thus has a public-sector fiscal responsibility to ensure sound financial management.
  Having never had core funding, CANADEM is reliant on project funding that can be quite variable, a further incentive to be financially risk-adverse.
3. CANADEM practices Integrated Risk Management:
  regularly assesses its current risk tolerance, e.g. the sufficiency of its operational reserve;
  identifies and quantifies risks, then effects risk mitigation measures;
  designates Primaries, activity teams, and organization-wide cohesion on how to identify and address risk;
  manages risks events so as to avoid or limit actual harm.
CANADEM
Integrated Risk Management Doctrine & Procedures
Rev. Aug 2015
Notes: CANADEM Risk - a possible future event that can substantially harm or benefit

## Slide 2: CANADEM’s 3 Key Risk Sectors
Financial
Risk
Operational
Risk
Strategic
Risk
see notes
Notes: Strategic Risk is the most important, because if there is not an excellent reason for doing something, why would we. We are not in the business of busy work, we are in the business of useful work.
Operational Risk is #2, because if we cannot make good things happen on the ground, then again, what are we doing.
Financial Risk is #3 and while a sine qua non (without which we cannot function for long), we are not in this for the money.

## Slide 3: Three Risk Analysis Factors
Level of Risk = Likelihood x Impact (part math and part intuition)
#1 Likelihood
of risk occurring
e.g. 50%, 2%, 00.1% ?
#2 Impact
if risk occurs
catastrophic to simply annoying?
Level of Acceptable Risk
#3 Acceptability -comfort level with risk by board & staff
STOP?
or
GO?

## Slide 4: Risk Assessment Process
Monitor and Review Risk
1. Identify risk mitigation
2. Develop risk mitigation
3. Implement risk mitigation
Accept
Risk
Is Inherent Risk Acceptable?
Is Residual Risk Acceptable?
That’s right, you can never get rid of all of the risk short of not undertaking a particular activity.
YES
NO
YES
restart the risk mitigation process
Risk increases
or changes?
Risk is so unlikely and of such minor impact that no risk mitigation is necessary
Do NOT accept risk: end project, action, proposal, etc.
NO
?

## Slide 5: Integrated Risk Management (IRM) Informal Discussion Points
There is no return without risk
  Rewards go to those who take acceptable risks
Communicate and ask questions
  Search out & openly discuss risks
Know what you don't know
  Question your assumptions & adapt your actions
Use common sense and avoid ‘decidophobia’
  Better to be roughly right than precisely wrong through inaction or a decision that is too late
One for all, all for one
  Only integrated teams achieve integrated risk management.
1. IRM procedures for the uninitiated can start to confuse, when in fact the basics are simple; 2. These discussion points are designed for individuals coming new to IRM.

## Slide 6: Some Risk Mitigation Measures or Approaches
Prevention: e.g. stop or ban the activity
Reduction: e.g. limit the activity
Redundancy: e.g. back-ups, duplicate systems/equipment.
Controls: e.g. multiple sign-offs, check-lists
Transfer: e.g. by contract to transfer risk to consultants, insurers, etc.
Planning: e.g. contingency plans, operations gaming
Financial Reserves: e.g. ability to self-finance contingency actions
Training: e.g. individuals and teams trained for what might happen
*Risk Management is NOT the same as Crisis Management
This partial list of risk mitigation measures shows that risk management is systemic, constant, and a normal business activity.
Only very occasionally will risk events escalate into crisis management. So having frequent crises indicates either particularly bad luck or ineffective risk management to avoid crises.

## Slide 7: CANADEM a Resilient Organization (based on staff capacity, not doctrine)
A key CANADEM value-added comes from being a resilient organization that
adapts well to risk,
learns from mistakes, and
can be relied upon to make it happen when dealing with:
    External Risks: high awareness of its operating environment, able to identify changes in external risks, and dynamically reinventing procedures and strategies;
    Unexpected Risks: Withstand unexpected sudden change and instantly adapt;
    Internal Risks: Internally networked and self-aware so as to rapidly detect new internal risks or errors, and take immediate corrective action.
CANADEM’s resilience in Integrated Risk Management comes from an empowered staff trained in 3 key CANADEM operational principles or attitudes:
    Subsidiarity Principle of delegated authority
    Primaries designated for all responsibilities
    Team Culture including an all-of-CANADEM
      360° alert & support approach , i.e. Integrated Risk Management.
WHY?

## Slide 8: Reason (HEAD) versus Feeling (GUT) Some Psychological Risk Identification Mistakes Read Risk: The Science and Politics of Fear by Dan Gardner
Calm informed analysis mitigates
partial facts and/or intuition and/or emotion
Availability Bias
“I remember a risk so it is more likely”
Anchoring and Adjustment heuristic – we guess at level of risk using a recent number then adjust insufficiently
“heard it on the news so it is more likely to happen”
Some hard data does not mean that there is risk
Familiarity breeds contempt – won’t happen to me.
Group Polarization
AKA group think: people with same perspective when in a group become more convinced and less open to new info
Confirmation Bias
We hear what we want…
to confirm what we already believe
Lack of hard data to quantify a risk does not mean there is no risk
Law of Similarity
Appearance equals reality (“it walks like a duck”)
SMART DECISIONS
Rule of typical things: some details are plausible therefore the whole scenario is likely
A ‘risk’ is not a risk just because someone has a gut feeling

## Slide 9: Remember other related CANADEM Procedures/Policies…
…such as

## Slide 10: CANADEM Risk Management Roles & Responsibilities
Board: Strategic direction on risk tolerance and risk management.
Executive Director
  Cultivate a culture of risk management, sensible risk taking, and team cohesion with all-of-CANADEM 360° alert & support as part of CANADEM’s Integrated Risk Management;
  Ensure strategic risks are identified, assessed, and managed;
  Operational Risk – can delegate yet ED retains ultimate responsibility for all risks.
    Provide guidance on operational risk management;
    Engaged by Primaries as required for operational risk management.
Division/Unit Heads
  Ensure division/unit operational risks are identified, assessed, and managed;
  Cultivate a culture of risk management, sensible risk taking, and team cohesion with all-of-CANADEM 360° alert & support.
All CANADEM Personnel
    Stay informed on risk management issues related to their operational piece;
    Accept risk as part of daily business & take prompt action as risk materializes.
    Understand and implement all-of-CANADEM 360° alert and support
All-of-CANADEM 360° alert & support
A core CANADEM operational principle that every individual is key to effective Integrated Risk Management (IRM). Regardless of position, every individual is key to mitigating every CANADEM risk by alerting others if they perceive risks, and supporting others to manage risks.

## Slide 11: Risk Assessment Matrix
 | Minor | Moderate | Major
Likely | moderate | high | critical
Possible | low | moderate | high
Unlikely | low | low | moderate
Money transfer blocked or delayed
Deployee killed or seriously injured
strong negative audit comments
Project substantially over budget
IMPACT
PROBABILITY
personal information files hacked
High maintenance deployee wastes our time
High maintenance deployee wastes (UN) mission’s time
Deployee mugged or in minor car accident
Deployee misses flight or looses money, e.g. pick pocket
DFATD triggers advance work by CANADEM and then does not fund the project.
Model matrix with some example risk events

## Slide 12: Liability & Limiting Liability
Every organization and/or individual involved in an activity/project has liability of some sort, as determined by their:
    Position or seniority;
    Role or function; and
    Reasonable expectation of their capacity and possible action.
Liability can be partially limited through contractual relationships.
  But courts are the final arbiter and will look to deny illegal or unfair liability-limitation by:
    the more powerful in an unequal bargaining relationship; and/or
    those in authority who should have been better informed, and who should have more effectively exercised their due diligence and duty of care.
Liability can never be fully limited.
Note that merely withdrawing from any activity will not avoid liability already incurred.

## Slide 13: ‘Org Chart’ of Liability for CANADEM Deployed Personnel (the CANPOL-Haiti I example)
UN DPKO
UN MINUSTAH
Cdn CIVPOL Contingent
Contingent Commander
CANADEM
CANPOL-Haiti
The 25 police experts themselves
Chef de mission
  Coordonnateur admin/log
RCMP
finance/admin control
command & control
information / coordination link
START
CIDA $ / FAC oversight
resultant liability of some sort
GoC & other member states
Teaching Point: everybody has some liability! And we mean everybody!

## Slide 14
GoC HoA Afg
CANADEM
Finance Division
CANADEM
Deployment Division
Technical Advisors
TAs and the CGSO management team are consultants on contract to CANADEM whose operational authority can at times approximate management control, and CANADEM always retains contractual control.
GoA
CANADEM
Roster Division
CGSO Director
LES Locally Engaged Staff
GoC Ottawa
CANADEM
Board
Administration & Logistics Manager
Operational authority (ranging from staff to consultants)
Strategic Oversight
Coordination Linkages & Information Sharing
Working link between CANADEM-HQ and CANADEM-CGSO
CANADEM Ottawa
Exec. Dir.
Security Team Leader
Deputy Director
MSU, guards, drivers
CANADEM CGSO Doctrine & Procedures 14
Always results in liability of some sort, albeit to varying degrees
‘Org Chart’ of Relative Liability for CANADEM Deployed Personnel CANADEM-CGSO Afghanistan May 2010
Notes: 14

## Slide 15: Legal Liability …can CANADEM be sued?
So far not, but yes we can be sued.
  The courts will decide if we have sufficiently met our duty of care.
  They look at the actual events, but know that nobody can prevent every risk event, so the courts, barring laws or contracts* to the contrary, will apply the ‘reasonable’ person test:
    Did CANADEM do everything that a ‘reasonable’ individual/agency would do to mitigate ‘reasonably’ likely events.
Can CANADEM prove (e.g. document) that we:
  Identified all ‘reasonably’ likely risks, e.g. documented ops gaming; and
  Have we legally (contractually*) transferred certain risks, e.g. through insurance, or to sub-contractors including consultants; and
  For all remaining risks did we take ‘reasonable’ mitigating measures such as
    a. Clear lines of authority & responsibility, with responsibilities set at the right level,
    e.g. subsidiarity and primaries;
    b. Risk and security analyses both initially, and then regularly reviewed/updated
    c. Resultant contingency plans and procedures (SOPs), also regularly reviewed/updated
    d. Sufficient training & information sharing with/between:
      All individuals so that they can mitigate risk
      Key staff so that they can mitigate risk and ensure that others are mitigating theirs.
* Contracts can inadvertently create liability that is greater than the ‘reasonable’ test applied by courts, so concise contracts may well be better than complicated contracts.

## Slide 16: Balancing risk management documentation against achieving other pressing tasks/goals
CANADEM since 2002 has effected substantial operational risk management but without much documentation of that risk management. This has two key drivers:
  Small team-minded staff where integrated risk management (IRM) is second nature;
  Operational principles/practices such as primaries and subsidiarity that enable ad hoc risk management that is both sufficient and an optimum allocation of resources to fit the requirements of rapid response and tight budgets.
So CANADEM is confident that its Integrated Risk Management is being achieved.
  Management & other Primaries are aware of and managing key strategic & operational risks; carrying out a risk assessments before making important decisions.
  All CANADEM staff have an understanding of CANADEM risk management doctrine. They are empowered to take smart decisions incurring risks, mitigate those risks, and know that they have the backing of management if risks materialize.
But such confidence is a risk in itself, and since our risk management process is not substantively documented, perhaps CANADEM is deceiving itself?
  One key mitigation is that CANADEM is self-aware of this risk of complacency and the need to further mitigate, e.g. IRM refresher training, or proactive ad hoc consideration of strategic and operational risk whenever there are key decisions or major events/trends
Notes: * A primary has the responsibility to ensure that a particular activity/function is carried out. Often many others including some senior to the primary are involved in that activity and are responsible to the primary to carry out certain tasks and thus the primary must manage them. Primaries are key to effective risk management, e.g. provide early warnings of new threats or risks that are materializing.

## Slide 17: Risk-Communication
Risk-communication can increased internal and external confidence by showing that:
CANADEM has a sound IRM (Integrated Risk Management) system;
has identified risks properly;
understands those risks; and
is taking sufficient mitigation measures.
Some risk-communication Myths and Realities | 
MYTH* | REALITY
Talking about risk will only alarm others. | Experienced outsiders know there are risks, and if well communicated by CANADEM, they will be reassured.
Risk is too complicated to explain to others. | IRM is based on common sense, and by using common language not techno-babble, CANADEM can explain CANADEM risk management to the public and other stakeholders.
Risk communications is the job of the communications people | Every CANADEM individual is part of IRM and can speak to their area of risk awareness and risk management. They may be the best spokesperson albeit with assistance and direction from senior management and communications people in order to retain a coherent CANADEM response.
* These myths stem from legitimate worries about risks inherent in any communications.
But silence when there should be communication and transparency is a mistake.
At the same time, like diplomacy, in some situations silence is the right risk mitigation.

## Slide 18: Emergency! Crisis! Death?! A Risk Event & CANADEM Response
Despite proper and sufficient risk prevention, bad things will happen, what is called a risk event.
All staff should be aware of our current response protocols
When a risk event occurs, staff should immediately look at those protocols
See: 2014-04 CANADEM HQ Critical Incident Response Immediate Procedure:
Z-drive/DOCTRINE and other core CANADEM Documents/2014-04 CANADEM HQ Critical Incident Response Procedure.doc
Throughout initial and subsequent actions, the principles in order of priority are:
Best interests of the victim and their immediate family
Concern about other CANADEM staff/associates in the field
Advancing optimum CANADEM and/or mission mitigation measures
Addressing CANADEM liabilities and risks
Transparency with the media and public without infringing privacy issues.

## Slide 19: CANADEM Critical Incident Fan-Out
YOU
Email all staff
Put out initial press release
Call Randy
Call Jill
Call Christine
Call Paul
Contact Board
Contact Field Mission
As per CANADEM’s Integrated Risk Management, any CANADEM staffer hearing of a critical incident will:
assume that nobody else is aware of it; and
take the immediate initiative of calling Paul+Christine+Jill
(see CANADEM HQ Critical Incident Response Immediate Procedure on z-drive)
Convene Response Team

## Slide 20: Note to non-CANADEM
Of course, feel free to use this powerpoint, and adapt it for your use. We hope it is useful.
Try watching it in slide show mode, as some slides have animations that you might find useful, and can easily go to the Animation Pane to build in pauses if you are training.
CANADEM’s in-house powerpoint is more extensive.
If you are interested in contracting CANADEM to help you customize this presentation or provide training assistance, please contact
Paul.LaRose-Edwards@CANADEM.ca

## Slide 21: END